## Cover
TASNETWORKS UNDERGROUND DEVELOPMENT (UD) AUDIT CHECKLIST (R389973)
COVER PAGE
TasNetworks Representative |  |  |  | UD Name (if applicable)
Developers Representative |  |  |  | UD Address Location
UD Ref No - CS_________ |  |  |  | UD Stage No
WASP ID |  |  |  | No of Lots
No of Stages
GATE OVERVIEW | SCHEDULED DATE |  | ACTUAL DATE PASSED |  | Comments relevant to the Gate Audit
GATE 1 Site Establishment Pre-Construction Audit
GATE 2 Civil Works Commence Audit
GATE 3 Conduit and Cable Audit
GATE 4 Street Furniture Audit
GATE 5 Reinstatement and Restoration Audit
GATE 6 Substation / HV Switchgear / Transformer Audit
GATE 7 Terminations, Labelling and Testing - Field, Design & Engineering Audit
TasNetworks Representative ______________________________ | DATE: | _____________________________
This UD is complete and has passed all field and testing audit requirements
Developer Representative: ______________________________ | DATE: | _____________________________
This UD is complete and has passed all field and testing audit requirements

## G1
TASNETWORKS UNDERGROUND DEVELOPMENT (UD) AUDIT CHECKLIST (R389973)
GATE 1 Site Establishment Pre-Construction Audit
DATE
Item No | Audit Question | Reference Document | Details on Conditional Proceed or Hold |  | Photograph Evidence Requried | Hold | Conditional Proceed | Pass and Proceed
1.1 | Attend and complete Developers Site Induction | Specification |  |  | No
1.2 | Sight Developer Civil and Electrical contractors to be engaged - confirm AEC status | Design |  |  | No
1.3 | Sight Certificate of Design Acceptance URD | Design |  |  | No
1.4 | Sight and confirm Current Version of Design | Specification |  |  | No
1.5 | Is the Site Secure as Practical? | Design |  |  | No
1.6 | Boundary pegs and road reserves marked on site? | On site |  |  | Yes
1.7 | Has the correct Substation been ordered? | Design |  |  | No
All Field Audit Criteria passed and accepted |  |  |  | Date of Developer Requested Site Audit
TasNetworks Site Representative |  |  |  | Date Passed / Accepted
Developer Representative |  |  |  | Date Passed / Accepted

## G2
TASNETWORKS UNDERGROUND DEVELOPMENT (UD) AUDIT CHECKLIST (R389973)
GATE 2 CIVIL WORKS COMMENCE AUDIT
DATE
ITEM | AUDIT QUESTION | Reference Document | Details on Conditional Proceed or Hold |  | Photograph Evidence Requried | Hold | Conditional Proceed | Pass and Proceed
2.1 | Is Trenching to Alignment and Depth? | Design & Specification |  |  | Yes
2.2 | Have Open Trenches been Surveyed? | Specification |  |  | No
2.3 | Have Trenches been Excavated as per the Approved Design? | Design |  |  | No
2.4 | Confirm that the new Electrical conduit is at accepted clearance from other infrastructure | Design & Specification |  |  | Yes
2.5 | Has the Substation Earth Mat been installed as per the Approved Design? (Also in Gate 6) | Design |  |  | Yes
2.6 | Has the correct bedding material for the trench been utilised? | Specification |  |  | Yes
2.7 | Has the correct Trench Backfilling process been followed? | Specification |  |  | Yes
2.8 | Have waterways been protected from site run off? | Developer documents |  |  | No | Notes only
2.9 | Are Street Furniture foundations located as per the Approved Design? | Design |  |  | No
2.1 | Confirm Street Light Cabinets have approved footings, level aligned prior to concrete foundation installation | Specification |  |  | Yes
2.11 | Is the orientation and height of the Street Light Hold Down Bolts correct? | Design |  |  | No
2.12 | Confirm Street Light hold down bolts thread protection installed? | Specification |  |  | Yes
2.13 | Is the Street Furniture conduit depth and direction correct? | Design |  |  | No
2.14 | Confirm Street Light foundations, concrete pad are compacted and at correct depth | Specification |  |  | Yes
2.15 | Confirm Bedding Material for Street Furniture accepted? | Specification |  |  | Yes
2.16 | Confirm Street Furniture foundations been compacted? | Specification |  |  | Yes
2.17 | As applicable, bore logs accuracy for depth and alignment? | Developer documents |  |  | No
2.18 | Is the size of bore pipe correct? | Specification |  |  | No
2.19 | Have bore activities been installed as per the Approved Design? | Design |  |  | No
All Field Audit Criteria passed and accepted |  |  |  | Date of Developer Requested Site Audit
TasNetworks Site Representative |  |  |  | Date Passed / Accepted
Developer Representative |  |  |  | Date Passed / Accepted

## G3
TASNETWORKS UNDERGROUND DEVELOPMENT (UD) AUDIT CHECKLIST (R389973)
GATE 3 CONDUIT AND CABLE AUDIT
DATE
ITEM | AUDIT QUESTION | Reference Document | Details on Conditional Proceed or Hold |  | Photograph Evidence Requried | Hold | Conditional Proceed | Pass and Proceed
3.1 | Have Conduit(s) been installed as per the Approved Design? | Design & Specification |  |  | Yes
3.2 | Have Cables(s) been installed as per the Approved Design? | Design & Specification |  |  | No
3.3 | Have conduits joints been installed correctly? | Design & Specification |  |  | Yes
3.4 | Has Mechanical Protection cover been installed as per the Approved Design? | Design |  |  | Yes
3.5 | Has the caution marker tape been installed as per the approved Design? | Design |  |  | Yes
3.6 | Are minimum clearances maintained for Conduit Cross Overs? | Design |  |  | Yes
3.7 | Are Cable Cross Overs maintained? | Design |  |  | Yes
3.8 | Are Clearances to other underground Infrastructure Compliant? | Design |  |  | Yes
3.9 | Has the correct bedding material been utilised for conduit? | Specification |  |  | Yes
3.1 | Is the bedding material installed as per the Approved Design for Direct Buried cable? | Design |  |  | Yes
3.11 | Has the cabling been lubricated before being installed in conduits? | Specification |  |  | No
3.12 | Has Conduit been proved prior to Cable Hauling and a draw rope retained? | Specification |  |  | Yes
3.13 | Has the correct Backfilling process been followed as per the design? | Design |  |  | Yes
3.14 | Are the Correct Conduit Bends and Pits being utilised? | Specification |  |  | Yes
3.15 | Have surface Cable Markers been installed if applicable? | Design |  |  | Yes
3.16 | Confirm Cable bend radius have been maintained | Specification |  |  | Yes
3.17 | Sight cable installation equipment - equipment complies with hauling tension requirements and has not been exceeded? | Specification |  |  | No
3.18 | Are Cable Joints as per design, using approved jointing kit and accredited cable jointer? | Design |  |  | Yes
All Field Audit Criteria passed and accepted |  |  |  | Date of Developer Requested Site Audit
TasNetworks Site Representative |  |  |  | Date Passed / Accepted
Developer Representative |  |  |  | Date Passed / Accepted

## G4
TASNETWORKS UNDERGROUND DEVELOPMENT (UD) AUDIT CHECKLIST (R389973)
GATE 4 STREET FURNITURE AUDIT
DATE
ITEM | AUDIT QUESTION | Reference Document | Details on Conditional Proceed or Hold |  | Photograph Evidence Requried | Hold | Conditional Proceed | Pass and Proceed
4.1 | Is the Street Furniture Location and Type as per the Approved Design? | Design |  |  | Yes
4.2 | Is the Street Furniture suitable for service - not damaged? | On site |  |  | Yes
4.3 | Has the Electrical Street Furniture been Surveyed? GPS coordinate required for Handover | Specification |  |  | No
4.4 | Is the Street Furniture installation Height Correct? | Design & Specification |  |  | No
4.5 | Is the Street Furniture fixed to bases or foundations correctly? | Specification |  |  | Yes
4.6 | Is the Street Furniture plumb and aligned correctly? | Specification |  |  | Yes
4.7 | Has Street Furniture cable penetrations and entries been sealed appropriately? | Specification |  |  | Yes
All Field Audit Criteria passed and accepted |  |  |  | Date of Developer Requested Site Audit
TasNetworks Site Representative |  |  |  | Date Passed / Accepted
Developer Representative |  |  |  | Date Passed / Accepted

## G5
TASNETWORKS UNDERGROUND DEVELOPMENT (UD) AUDIT CHECKLIST (R389973)
GATE 5 REINSTATEMENT AND RESTORATION AUDIT
DATE
ITEM | AUDIT QUESTION | Reference Document | Details on Conditional Proceed or Hold |  | Photograph Evidence Requried | Hold | Conditional Proceed | Pass and Proceed
5.1 | Has site restoration been completed where Electrical Infrastructure installation activities have occurred? (Site make good/better including roads, footpaths, driveways, plants…) | Specification |  |  | Yes
5.2 | Has the potential for subsidence and erosion been minimised to Electrical Infrastructure installation activities? Mounding and Surface Fracking Evidence | Specification |  |  | Yes
5.3 | Have Substation retaining Walls and drainage be installed as per the Approved Design? | Specification |  |  | Yes
All Field Audit Criteria passed and accepted |  |  |  | Date of Developer Requested Site Audit
TasNetworks Site Representative |  |  |  | Date Passed / Accepted
Developer Representative |  |  |  | Date Passed / Accepted

## G6
TASNETWORKS UNDERGROUND DEVELOPMENT (UD) AUDIT CHECKLIST (R389973)
GATE 6 SUBSTATION / HV SWITCHGEAR / TRANSFORMER AUDIT
DATE
ITEM | AUDIT QUESTION | Reference Document | Details on Conditional Proceed or Hold |  | Photograph Evidence Requried | Hold | Conditional Proceed | Pass and Proceed
6.1 | Sight Factory Acceptance Tests Substation (LV switchgear, HV switchgear, and transformer) | Specification |  |  | No
6.2 | Has the correct Substation been installed? | Design |  |  | No
6.3 | Has the Substation Earth Mat been installed as per the Approved Design? | Design |  |  | Yes
6.4 | Substation locked/secured. | On site |  |  | Yes
6.5 | Is the Substation suitable for service - not damaged? | On site |  |  | Yes
6.6 | Has the Correct Substation plinth been installed? | On site |  |  | Yes
6.7 | Has the correct Substation been installed? | On site |  |  | Yes
All Field Audit Criteria passed and accepted |  |  |  | Date of Developer Requested Site Audit
TasNetworks Site Representative |  |  |  | Date Passed / Accepted
Developer Representative |  |  |  | Date Passed / Accepted

## G7
TASNETWORKS UNDERGROUND DEVELOPMENT (UD) AUDIT CHECKLIST (R389973)
GATE 7 TERMINATIONS, LABELLING AND TESTING - Field, Design & Engineering Audit
DATE
ITEM | AUDIT QUESTION |  | Reference Document | Details on Conditional Proceed or Hold |  | Photograph Evidence Requried | Hold | Conditional Proceed | Pass and Proceed
7.1 | Is all the Site Earthing installed as per the Approved Design? |  | Design |  |  | Yes
7.2 | Is Earth Labelling as per the Approved Design? Compliance to AS3000 |  | Design |  |  | Yes
7.3 | Confirm Street Furniture Fuse Panels are wired and fitted correctly? |  | Specification |  |  | No
7.4 | Are Street Furniture Terminations and Connections acceptable? |  | Specification |  |  | Yes
7.5 | Have Street Furniture Fuses been installed and to Approved Design correct rating? |  | Design |  |  | No
7.6 | Are Street furniture MEN connections installed as per design? |  | Design |  |  | Yes
7.7 | Are there any Street Furniture cable joints? - TasNetworks requirement that all cabling must be continuous with no joints. Any joints are an exception and are as per Design |  | Design |  |  | No
7.8 | Is the Street Furniture numbered and labelled correctly as per design (cabinets and turrets only)? |  | Design |  |  | Yes
7.9 | Have all Street Furniture Cable and Termination covers been installed? |  | Specification |  |  | Yes
7.1 | Are all Substation cable terminations correct and all circuits labelled? |  | Design |  |  | Yes
7.11 | Are the Substation Circuit Breaker Ratings and Settings Correct as per the design? |  | Design |  |  | No
7.12 | Compare Survey Plan against Red Line Drawings |  | Design & Speciifcation |  |  | No
7.13 | Has Developer's certificates of completion (civil and electrical) been delivered to TasNetworks Customer Representative |  | Contract |  |  | No
7.14 | Are all earthing test results acceptable to TasNetworks Standards? |  | Specification |  |  | No
7.15 | Substation/HV switchgear Earth testing must be witnessed by TasNetworks |  | Specification |  |  | No
7.16 | Has Street Furniture Electrical Compliance Testing been completed to TasNetworks Standards and witnessed? |  | Specification |  |  | No
7.17 | Performance security received - check with Case manager |  | Contract | This item cannot be conditionally passed |  | No
7.18 | Switching sheet by the developer received and approved by TasNetworks |  | Contract | This item cannot be conditionally passed |  | No
All Field, Labelling, Terminations and Testing Audit Criteria passed and accepted |  |  |  |  | Date of Developer Requested Site Audit
TasNetworks Site Representative |  |  |  |  | Date Passed / Accepted
TasNetworks Designer / Engineer
Developer Representative
Development approved for Commissioning
Project Manager to sign-off
Note on A3: Jarad Hughes: Split up, electrical testing to go to engineer/designer, other for the auditors